## Runbook
Cutover runbook
PRAG-DEL-SOL-ONE Ltd · free template · adapt to your own governance
Task ID | Phase | Task | Owner | Backup | Depends on | Planned start | Duration (mins) | Planned end | Actual start | Actual end | Completion check | Status | Notes
C001 | Freeze | Announce change freeze and confirm all users logged out of legacy system | Service desk lead |  |  |  | 30 |  |  |  | Freeze notice sent; active sessions = 0 | Not started
C002 | Extract | Run final extract from legacy system | Supplier DBA |  | C001 |  | 180 |  |  |  | Extract log complete; record counts captured | Not started
C003 | Validate | Reconcile migrated record counts against extract | Data migration lead |  | C002 |  | 90 |  |  |  | Counts within agreed tolerance | Not started
C004 | Go/no-go | Go/no-go checkpoint call | Programme manager |  | C003 |  | 30 |  |  |  | Decision recorded with criteria status | Not started

## Contacts
Cutover contacts and escalation
PRAG-DEL-SOL-ONE Ltd · free template · adapt to your own governance
Role | Name | Organisation | Phone | On shift (from-to) | Escalates to

## Go-no-go
Go/no-go criteria
PRAG-DEL-SOL-ONE Ltd · free template · adapt to your own governance
Area | Criterion | Owner | RAG | Evidence | Comment
Technical | All environments built and interfaces tested end to end
Data | Migration reconciled within agreed tolerances
People | Training completion above agreed threshold
Support | Hypercare rota staffed; escalation routes published
Safety | Clinical safety case signed off by the clinical safety officer