## Summary
RAID summary for board packs
Counts update automatically from the four log tabs.
Measure | Count
Open risks
Open risks scoring 15+
Open issues
High-priority open issues
Assumptions not yet confirmed
Dependencies at risk or late
Scoring: likelihood x impact. 15+ red, 8-14 amber, 1-7 green.

## Risks
Risk log
PRAG-DEL-SOL-ONE Ltd · free template · adapt to your own governance
ID | Date raised | Risk (cause, event, effect) | Category | Owner | Likelihood (1-5) | Impact (1-5) | Score | Response | Mitigating actions | Action due | Status | Last reviewed
R001 |  | Example: Because the legacy system holds duplicate patient records, the migration may fail reconciliation, delaying go-live by up to four weeks. | Data | Data migration lead | 3 | 4 |  | Reduce | Run duplicate-record cleanse before rehearsal 1; agree reconciliation tolerances with information governance. |  | Open

## Issues
Issue log
PRAG-DEL-SOL-ONE Ltd · free template · adapt to your own governance
ID | Date raised | Issue | Impact | Priority | Owner | Action | Due | Status | Resolution

## Assumptions
Assumption log
PRAG-DEL-SOL-ONE Ltd · free template · adapt to your own governance
ID | Assumption | Owner | Confirm by | Confirmed? | Risk if false | Notes

## Dependencies
Dependency log
PRAG-DEL-SOL-ONE Ltd · free template · adapt to your own governance
ID | We need | From (party) | Their contact | Needed by | Our owner | Status | Notes